## Sheet1
Today's date: | 2024-07-30
Project ID | Project Name | Sub-Portfolio | ESP Leader | Project Status | Overall Health | Blank Column | Service Category | Project Start Date | Datevalue Project Start Date | Project End Date | Datevalue Project End Date | Radar ID | %Project Duration Completed2
P107232 | Project abc | InfoSec Management Services | Kris Jennings | Active | GREEN |  | InfoSec Program Support | 2023-08-21 08:00 | 45159.3333 | 01-31-25 | 45688 | 1 | 65.01%
P105891 | Project bcd | Asset & Data Protection | Donna Nufrio | Active | GREEN |  | InfoSec Program Management | 2024-06-28 08:00 | 45471.3333 | 07-26-24 | 45499 | 2 | 100%
P107295 | Project cde | IAM Services | Patrick Allen | Active | GREEN |  | Identity and Access | 2024-02-19 08:00 | 45341.3333 | 10-18-24 | 45583 | 3 | 66.9%
P103606 | Project def | IAM Services | Patrick Allen | Active | GREEN |  | Identity and Access | 2024-01-22 08:00 | 45313.3333 | 02-17-25 | 45705 | 4 | 48.43%
P107291 | Project efg | IAM Services | Patrick Allen | On Hold | GREEN |  | Identity and Access | 2023-09-05 08:00 | 45174.3333 | 08-30-24 | 45534 | 5 | 91.38%
P107428 | Project zyx | Transformation Programs | Yana Kirksey | Closed | Closed |  | Threat Management | 2023-08-21 08:00 | 45159.3333 | 11-09-23 | 45239 | 6 | 100%
P107779 | Project fgh | IAM Services | Patrick Allen | Active | GREEN |  | Identity and Access | 2023-08-21 08:00 | 45159.3333 | 09-25-24 | 45560 | 7 | 85.77%
P107601 | Project yxw | Transformation Programs | Yana Kirksey | Closed | Closed |  | Threat Management | 2023-06-24 08:00 | 45101.3333 | 12-18-23 | 45278 | 8 | 100%
P108066 | Project ghi | IAM Services | Patrick Allen | Active | GREEN |  | Identity and Access | 2024-03-07 08:00 | 45358.3333 | 07-30-24 | 45503 | 9 | 100%
P107132 | Project hij | IAM Services | Patrick Allen | Active | GREEN |  | Identity and Access | 2024-06-10 08:00 | 45453.3333 | 11-22-24 | 45618 | 10 | 30.16%
P106393 | Project ijk | IAM Services | Patrick Allen | Active | GREEN |  | Identity and Access | 2024-06-17 08:00 | 45460.3333 | 09-27-24 | 45562 | 11 | 41.97%
P108323 | Project jkl | Transformation Programs | Yana Kirksey | Active | GREEN |  | Threat Management | 2021-09-01 08:00 | 44440.3333 | 07-31-24 | 45504 | 12 | 99.91%
P107875 | Project klm | InfoSec Management Services | Kris Jennings | Active | GREEN |  | InfoSec Program Support | 2023-09-25 08:00 | 45194.3333 | 10-25-24 | 45590 | 13 | 78.01%
P107876 | Project 123 | InfoSec Management Services | Kris Jennings | Active | Amber |  | InfoSec Program Support | 2023-09-25 08:00 | 45194.3333 | 10-25-24 | 45590 | 13 | 78.01%
P107877 | Project Twinkle Toes | InfoSec Management Services | Kris Jennings | Active | ON HOLD |  | InfoSec Program Support | 2023-09-25 08:00 | 45194.3333 | 10-25-24 | 45590 | 13 | 78.01%
| c1 |  |  |  | RED |  | Threat Management | [5 empty] | 1
| c2 |  |  |  | RED |  | Threat Management | [5 empty] | 1
| c3 |  |  |  | RED |  | Threat Management | [5 empty] | 1
| o1 |  |  |  | RED |  | InfoSec Program Support | [5 empty] | 0.77
| o2 |  |  |  | RED |  | InfoSec Program Support | [5 empty] | 0.77
| a1 |  |  |  | GREEN |  | InfoSec Program Support | [5 empty] | 0.77
| a2 |  |  |  | GREEN |  | InfoSec Program Support | [5 empty] | 0.77
| a3 |  |  |  | Amber |  | InfoSec Program Support | [5 empty] | 0.77
| a4 |  |  |  | GREEN |  | InfoSec Program Support | [5 empty] | 0.77
| a5 |  |  |  | RED |  | InfoSec Program Support | [5 empty] | 0.77
| q1 |  |  |  | RED |  | InfoSec Protection Services | [5 empty] | 0
| q2 |  |  |  | RED |  | IT Risk Management | [5 empty] | 0
| q3 |  |  |  | RED |  | Identity and Access | [5 empty] | 0
| q4 |  |  |  | RED |  | Threat Management | [5 empty] | 0
| q5 |  |  |  | RED |  | InfoSec Program Management | [5 empty] | 0
| q6 |  |  |  | RED |  | InfoSec Program Support | [5 empty] | 0
| q7 |  |  |  | RED |  | Security Design Services | [5 empty] | 0
| q8 |  |  |  | RED |  | Compliance & Assurance | [5 empty] | 0